## Dashboard
Azure DevOps / AKS Deployment Project — Dashboard
Last Updated: March 06, 2026
Phase | Owner | Priority | % Complete | Status | Start Date | End Date | Open Tasks | Blocked | Notes
Build | TBD | P2 - High | 0% | Not Started | TBD | TBD | 14 | 0
Application | TBD | P2 - High | 0% | Not Started | TBD | TBD | 10 | 0
Security | TBD | P1 - Critical | 0% | Not Started | TBD | TBD | 10 | 0
Operationalisation | TBD | P3 - Medium | 0% | Not Started | TBD | TBD | 10 | 0
Compliance | TBD | P1 - Critical | 0% | Not Started | TBD | TBD | 7 | 0
Documentation | TBD | P3 - Medium | 0% | Not Started | TBD | TBD | 10 | 0
PHASE LEGEND |  |  | STATUS LEGEND |  |  | PRIORITY LEGEND
| Build |  |  | Not Started |  |  | P1 - Critical
| Application |  |  | In Progress |  |  | P2 - High
| Security |  |  | Complete |  |  | P3 - Medium
| Operationalisation |  |  | Blocked |  |  | P4 - Low
| Compliance |  |  | At Risk
Documentation

## Project Overview
Project Overview — AWS Health Notification Remediation
Update Status and % Complete weekly. Use dropdowns for Phase, Owner, Priority and Status.
# | Phase | Task | Assigned To | Priority | Status | % Done | Start | Due | Dependencies | Requested By | Technology | Team | Notes
1 | Build | Azure DevOps Organisation & Project setup | Cloud Engineer | P1 - Critical | Not Started | 0% | 2025-03-01 | 2025-03-07 |  |  |  |  | Create ADO org, project, repos and branch policies
2 | Build | Azure Container Registry (ACR) provisioning | Cloud Engineer | P1 - Critical | Not Started | 0% | 2025-03-05 | 2025-03-10 | Task 1 |  |  |  | Enable geo-replication and private endpoint
3 | Build | AKS cluster provisioning — system node pool | Cloud Engineer | P1 - Critical | Not Started | 0% | 2025-03-08 | 2025-03-20 | Task 2 |  |  |  | RBAC enabled, private cluster, CNI networking
4 | Build | AKS user node pools — workload sizing | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-15 | 2025-03-22 | Task 3 |  |  |  | Separate pools per workload type; autoscale enabled
5 | Build | Azure Virtual Network (VNet) and subnet design | Cloud Engineer | P1 - Critical | Not Started | 0% | 2025-03-01 | 2025-03-07 |  |  |  |  | Hub-spoke topology; dedicated AKS subnet
6 | Build | Azure Firewall — policy and rule collection groups | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-08 | 2025-03-15 | Task 5 |  |  |  | Egress rules for AKS, ACR, Key Vault, ADO agents
7 | Build | Network Security Groups (NSGs) per subnet | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-08 | 2025-03-14 | Task 5 |  |  |  | Deny-all default; allow only required ports
8 | Build | Private Endpoints — ACR, Key Vault, Service Bus | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-12 | 2025-03-19 | Tasks 5-7 |  |  |  | Disable public access after PE creation
9 | Build | Azure Key Vault provisioning and access policies | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-08 | 2025-03-14 | Task 5 |  |  |  | Soft-delete, purge protection enabled; RBAC auth mode
10 | Build | Azure Service Bus namespace and topics | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-15 | 2025-03-21 | Task 8 |  |  |  | Premium tier for VNet integration; health event routing
11 | Build | ADO self-hosted agent pool on AKS | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-20 | 2025-03-27 | Tasks 3,6 |  |  |  | Agents run as pods; access to ACR and Key Vault
12 | Build | Helm chart development — application workloads | Developer | P2 - High | Not Started | 0% | 2025-03-22 | 2025-04-04 | Tasks 3,9 |  |  |  | Parameterise per environment; secrets from Key Vault
13 | Build | Infrastructure as Code — Terraform modules | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-01 | 2025-03-28 |  |  |  |  | Modules: AKS, ACR, Firewall, VNet, KV, Sentinel
14 | Build | Terraform remote state — Azure Storage Account | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-01 | 2025-03-05 |  |  |  |  | State locking via blob lease; versioning enabled
15 | Application | ADO Pipeline — CI build and container image publish | Developer | P2 - High | Not Started | 0% | 2025-04-01 | 2025-04-10 | Tasks 2,11 |  |  |  | YAML pipeline; image scanning gate before push to ACR
16 | Application | ADO Pipeline — CD deploy to AKS via Helm | Developer | P2 - High | Not Started | 0% | 2025-04-05 | 2025-04-14 | Task 15 |  |  |  | Blue-green or rolling; approval gate for prod
17 | Application | ADO Pipeline — Terraform plan/apply with approval gate | Cloud Engineer | P2 - High | Not Started | 0% | 2025-04-01 | 2025-04-10 | Task 13 |  |  |  | Separate pipelines per environment
18 | Application | Container image hardening — base image standards | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-25 | 2025-04-04 | Task 2 |  |  |  | Distroless or minimal base; no root user
19 | Application | Kubernetes manifests — resource limits and requests | Developer | P3 - Medium | Not Started | 0% | 2025-04-01 | 2025-04-10 | Task 12 |  |  |  | Set CPU/memory limits on all containers
20 | Application | Kubernetes RBAC — service accounts and role bindings | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-22 | 2025-03-28 | Task 3 |  |  |  | Least privilege; no cluster-admin for workloads
21 | Application | Workload Identity — Azure AD pod identity | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-22 | 2025-03-28 | Tasks 3,9 |  |  |  | Replace service principal secrets with managed identity
22 | Application | Ingress controller — Application Gateway / NGINX | Cloud Engineer | P2 - High | Not Started | 0% | 2025-04-05 | 2025-04-14 | Tasks 3,7 |  |  |  | TLS termination; WAF policy attached
23 | Application | Horizontal Pod Autoscaler (HPA) configuration | Developer | P3 - Medium | Not Started | 0% | 2025-04-10 | 2025-04-17 | Task 19 |  |  |  | CPU and memory based scaling per workload
24 | Application | Multi-environment config — Dev / Non-Prod / Prod | Developer | P2 - High | Not Started | 0% | 2025-04-01 | 2025-04-10 | Task 12 |  |  |  | Separate namespaces or clusters per env
25 | Security | Azure Entra ID — groups, roles, and RBAC assignments | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-01 | 2025-03-14 |  |  |  |  | No direct user assignments; use groups only
26 | Security | Azure Policy — deny non-compliant resource deployments | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-15 | 2025-03-28 | Task 25 |  |  |  | Built-in initiatives: CIS, NIST, Protected B
27 | Security | Microsoft Defender for Cloud — all plans enabled | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-10 | 2025-03-17 |  |  |  |  | Enable Defender for Containers, Key Vault, DNS, ARM
28 | Security | Microsoft Defender for Containers — AKS integration | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-17 | 2025-03-24 | Tasks 3,27 |  |  |  | Runtime threat detection; image vulnerability scanning
29 | Security | Microsoft Sentinel — workspace and data connectors | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-10 | 2025-03-24 |  |  |  |  | Connect: AAD, Defender, AKS, Firewall, Activity Log
30 | Security | Sentinel — Analytics rules and MITRE ATT&CK mapping | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-24 | 2025-04-07 | Task 29 |  |  |  | Enable Fusion, anomaly rules; custom KQL rules for AKS
31 | Security | Sentinel — Playbooks (Logic Apps) for auto-remediation | Security Architect | P2 - High | Not Started | 0% | 2025-04-07 | 2025-04-18 | Task 30 |  |  |  | Auto-close low severity; notify on P1 incidents
32 | Security | Vulnerability management — Defender CSPM remediation | Security Architect | P2 - High | Not Started | 0% | 2025-03-24 | 2025-04-18 | Tasks 27,28 |  |  |  | Prioritise critical/high findings pre-go-live
33 |  | Secret rotation policy — Key Vault certs and secrets | Security Architect |  | Not Started | 0% |  | 2025-03-28 | Task 9 |  |  |  | Auto-rotation; alert on expiry < 30 days
34 | Security | DDoS Protection Standard — on hub VNet | Security Architect | P2 - High | Not Started | 0% | 2025-03-08 | 2025-03-15 | Task 5 |  |  |  | Enable on hub VNet; configure alerts
35 | Security | Privileged Identity Management (PIM) — JIT access | Security Architect | P1 - Critical | Not Started | 0% | 2025-03-15 | 2025-03-28 | Task 25 |  |  |  | No standing privileged access; require justification
36 | Operationalisation | Azure Monitor — Log Analytics workspace setup | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-10 | 2025-03-17 |  |  |  |  | Centralised workspace; 90-day retention minimum
37 | Operationalisation | Diagnostic settings — all resources to Log Analytics | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-17 | 2025-03-24 | Task 36 |  |  |  | AKS, Firewall, Key Vault, Service Bus, ACR
38 | Operationalisation | Azure Monitor Alerts — AKS cluster health | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-24 | 2025-03-31 | Tasks 36,37 |  |  |  | Node not ready, pod crash loop, OOM kill alerts
39 | Operationalisation | Azure Monitor Alerts — Firewall and NSG flow logs | Cloud Engineer | P2 - High | Not Started | 0% | 2025-03-24 | 2025-03-31 | Tasks 36,37 |  |  |  | Alert on denied traffic spikes
40 | Operationalisation | Application Insights — APM instrumentation | Developer | P3 - Medium | Not Started | 0% | 2025-04-10 | 2025-04-18 | Task 36 |  |  |  | SDK or auto-instrumentation per workload
41 | Operationalisation | Azure Monitor Workbooks — operational dashboard | Cloud Engineer | P3 - Medium | Not Started | 0% | 2025-04-07 | 2025-04-14 | Tasks 36-39 |  |  |  | AKS, Firewall, Defender, Sentinel summary
42 | Operationalisation | Runbook — AKS node drain and cordon procedure | Cloud Engineer | P2 - High | Not Started | 0% | 2025-04-14 | 2025-04-21 | Task 3
43 | Operationalisation | Runbook — Key Vault secret expiry response | Cloud Engineer | P3 - Medium | Not Started | 0% | 2025-04-14 | 2025-04-21 | Task 9
44 | Operationalisation | Runbook — Sentinel incident triage and escalation | Security Architect | P2 - High | Not Started | 0% | 2025-04-14 | 2025-04-21 | Task 29
45 | Operationalisation | On-call rotation and escalation path defined | Project Lead | P2 - High | Not Started | 0% | 2025-04-01 | 2025-04-07 |  |  |  |  | PagerDuty or ADO notification integration
46 | Compliance | Protected B control mapping to Azure services | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-15 | 2025-04-04 |  |  |  |  | Map ITSG-33 controls to Azure Policy, Defender, Sentinel
47 | Compliance | Azure Policy compliance report — baseline assessment | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-28 | 2025-04-07 | Task 26 |  |  |  | Identify non-compliant resources pre-go-live
48 | Compliance | Defender CSPM — regulatory compliance dashboard | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-28 | 2025-04-07 | Task 27 |  |  |  | Enable NIST 800-53, CIS Azure benchmarks
49 | Compliance | Audit log retention — 1 year minimum | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-17 | 2025-03-24 | Task 36 |  |  |  | Activity log, AAD sign-in, AKS audit logs
50 | Compliance | Data residency validation — Canada regions only | Compliance Officer | P1 - Critical | Not Started | 0% | 2025-03-10 | 2025-03-17 |  |  |  |  | Canada Central primary; Canada East DR
51 | Compliance | Risk acceptance sign-off — residual risks | Compliance Officer | P2 - High | Not Started | 0% | 2025-04-21 | 2025-04-28 | Tasks 46-50
52 | Compliance | Penetration test — pre-production sign-off | Security Architect | P1 - Critical | Not Started | 0% | 2025-04-21 | 2025-05-05 | Tasks 25-35 |  |  |  | Third-party or internal red team
53 | Documentation | Build doc — AKS cluster architecture and design | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-14 | 2025-04-25 | Task 3
54 | Documentation | Build doc — Azure Firewall rule set and topology | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-14 | 2025-04-25 | Task 6
55 | Documentation | Build doc — Terraform module catalogue | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-14 | 2025-04-25 | Task 13
56 | Documentation | Build doc — ADO pipeline design and approval gates | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-18 | 2025-04-28 | Tasks 15-17
57 | Documentation | Build doc — Entra ID RBAC and PIM configuration | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-18 | 2025-04-28 | Tasks 25,35
58 | Documentation | Ops runbook — AKS upgrade procedure | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-21 | 2025-04-30 | Task 3
59 | Documentation | Ops runbook — Sentinel incident response playbook | Tech Writer | P2 - High | Not Started | 0% | 2025-04-21 | 2025-04-30 | Task 44
60 | Documentation | Ops runbook — Disaster recovery and failover steps | Tech Writer | P2 - High | Not Started | 0% | 2025-04-25 | 2025-05-05 |  |  |  |  | Canada Central to Canada East failover procedure
61 | Documentation | Architecture overview diagram — full solution | Tech Writer | P3 - Medium | Not Started | 0% | 2025-04-25 | 2025-05-02 | All Build |  |  |  | Visio or draw.io; include network, identity, monitoring
62 | Documentation | End-user guide — ADO pipeline usage and approvals | Tech Writer | P4 - Low | Not Started | 0% | 2025-04-28 | 2025-05-07 | Tasks 15-17

## Risk Register
Risk Register
Risk ID | Phase | Risk Description | Likelihood | Impact | Risk Score | Mitigation | Owner | Status | Notes
R001 | Build | Lambda not triggered by Health events | Medium | High | #VALUE! | Update EventBridge pattern | TBD | Open
R002 | Security | Overprivileged IAM roles | Low | High | #VALUE! | Enforce least privilege | TBD | Open
R003 | Compliance | Protected B controls not met | Medium | High | #VALUE! | Map all controls before deployment | TBD | Open
R004 | Application | Multi-account deployment failure | Medium | High | #VALUE! | Test in non-prod first | TBD | Open
R005 | Operationalisation | No alerting on Lambda failures | High | High | #VALUE! | DLQ + CloudWatch alarm | TBD | Open
R006 | Documentation | Runbooks not maintained | Medium | Medium | #VALUE! | Assign doc owner per phase | TBD | Open

## Control List
Control List — Protected B & AWS Security Controls
Control ID | Category | Control Description | Phase | Owner | Implementation Status | Evidence Required | Due Date | Notes
C001 | Access Control | Least privilege IAM roles | Security | TBD | Not Started | IAM policy JSON
C002 | Access Control | MFA enforced on all accounts | Security | TBD | Not Started | IAM report
C003 | Audit & Logging | CloudTrail enabled all regions | Compliance | TBD | Not Started | CloudTrail config
C004 | Audit & Logging | CloudWatch log retention >= 90 days | Compliance | TBD | Not Started | Log group config
C005 | Data Protection | KMS encryption for SNS topics | Security | TBD | Not Started | KMS key policy
C006 | Data Protection | SES TLS enforced | Build | TBD | Not Started | SES config
C007 | Incident Response | DLQ configured on Lambda | Operationalisation | TBD | Not Started | Lambda config
C008 | Incident Response | Runbook documented and tested | Operationalisation | TBD | Not Started | Runbook doc
C009 | Vulnerability Mgmt | Lambda code scanning in CI/CD | Application | TBD | Not Started | CI/CD pipeline
C010 | Compliance | Protected B data classification | Compliance | TBD | Not Started | Classification doc
C011 | Network | VPC endpoints where applicable | Security | TBD | Not Started | VPC config
C012 | Change Mgmt | All changes via approved pipeline | Application | TBD | Not Started | Pipeline config

## Resources and Personnel
Resources and Personnel
Name | Role | Team | Phase Ownership | AWS Account Access | Availability | Contact | Notes
TBD | Project Lead | Cloud Ops | All Phases | Prod / Non-Prod / Dev | Full-time
TBD | Cloud Engineer | Infrastructure | Build, Application | Prod / Non-Prod | Full-time
TBD | Security Architect | Security | Security, Compliance | Non-Prod | Part-time
TBD | Compliance Officer | Risk & Compliance | Compliance | Read-only | Part-time
TBD | Developer | Application | Application | Non-Prod / Dev | Full-time
TBD | Technical Writer | Documentation | Documentation | Read-only | Part-time

## RACI Matrix
RACI Matrix
RACI LEGEND
Activity / Phase | Project Lead | Cloud Engineer | Security Architect | Compliance Officer | Developer | Tech Writer |  | R — Responsible
Build — Lambda Development | A | R | C | I | R | I |  | A — Accountable
Build — EventBridge Setup | A | R | C | I | C | I |  | C — Consulted
Application — IaC Templates | A | R | I | I | R | I |  | I — Informed
Application — CI/CD Pipeline | A | C | I | I | R | I
Security — IAM Review | C | C | R | I | I | I
Security — Threat Model | A | C | R | C | I | I
Operationalisation — Runbooks | A | R | C | C | C | R
Operationalisation — Monitoring | A | R | C | I | R | I
Compliance — Control Mapping | C | I | C | R | I | I
Compliance — Audit Evidence | A | C | C | R | I | I
Documentation — Build Docs | A | R | C | I | R | R
Documentation — Ops Runbooks | A | R | C | C | C | R

## Stack
Technology Stack — AWS Health Notification Solution
Component | Service / Tool | Type | Purpose | Phase | Account Scope | Version / Config | Notes
Kubernetes | Azure Kubernetes Service (AKS) | Azure PaaS | Run containerised workloads | Build | All envs | 1.29+; private cluster | System + user node pools
Container Registry | Azure Container Registry (ACR) | Azure PaaS | Store and scan container images | Build | All envs | Premium; geo-replicated | Private endpoint; image scanning
CI/CD | Azure DevOps Pipelines | Azure DevOps | Build, test, deploy automation | Application | All envs | YAML pipelines | Self-hosted agents on AKS
IaC | Terraform | OSS Tool | Provision all Azure infrastructure | Build | All envs | AzureRM provider | State in Azure Storage
Networking | Azure Virtual Network (VNet) | Azure PaaS | Hub-spoke network topology | Build | All envs | Hub-spoke | Dedicated AKS subnet
Firewall | Azure Firewall | Azure PaaS | Centralised egress and ingress control | Build | Hub VNet | Premium SKU | IDPS enabled; TLS inspection
Network Security | Network Security Groups (NSGs) | Azure PaaS | Subnet-level traffic filtering | Build | All envs | Flow logs enabled | Deny-all default rules
Private Access | Private Endpoints | Azure PaaS | Private connectivity to PaaS services | Build | All envs | Per service | ACR, KV, Service Bus, Storage
Secrets | Azure Key Vault | Azure PaaS | Secrets, certs, encryption keys | Build | All envs | RBAC auth mode | Soft-delete + purge protection
Messaging | Azure Service Bus | Azure PaaS | Health event routing and fan-out | Build | All envs | Premium; VNet integrated | Dead-letter queue enabled
Identity | Microsoft Entra ID (Azure AD) | Azure PaaS | IAM, RBAC, MFA, Conditional Access | Security | Tenant-wide | P2 licence | PIM for privileged roles
PAM | Privileged Identity Management (PIM) | Entra ID | Just-in-time privileged access | Security | Tenant-wide | Entra ID P2 | All admin roles in PIM
CSPM / CWPP | Microsoft Defender for Cloud | Azure PaaS | Security posture + threat protection | Security | All subscriptions | All plans enabled | Defender for Containers required
SIEM / SOAR | Microsoft Sentinel | Azure PaaS | Security event detection and response | Security | Central workspace | Analytics rules + playbooks | Connected to all data sources
Vuln Mgmt | Microsoft Defender Vulnerability Management | Azure PaaS | CVE scanning for images and nodes | Security | All envs | Integrated with Defender | ACR scanning + AKS runtime
Monitoring | Azure Monitor + Log Analytics | Azure PaaS | Centralised metrics, logs, alerts | Operationalisation | All envs | 90-day retention | All diag settings pointing here
APM | Application Insights | Azure PaaS | Application performance monitoring | Operationalisation | All envs | SDK / auto-instrument | Connected to Log Analytics WS
DDoS | Azure DDoS Protection | Azure PaaS | DDoS mitigation on public IPs | Security | Hub VNet | Standard plan
Policy | Azure Policy | Azure PaaS | Enforce compliance and governance | Compliance | Management group | Built-in + custom initiatives | CIS, NIST, Protected B
Ingress | Azure Application Gateway + WAF | Azure PaaS | L7 load balancing and WAF | Application | All envs | WAF v2; prevention mode | Attached to AKS ingress

## Documentation
Documentation Index
Doc ID | Phase | Document Name | Type | Owner | Status | Location / Link | Last Updated | Notes
D001 | Build | Lambda Architecture — Build Doc | Build Doc | TBD | Not Started | TBD
D002 | Build | EventBridge Rule Configuration — Build Doc | Build Doc | TBD | Not Started | TBD
D003 | Build | SES Domain Setup — Build Doc | Build Doc | TBD | Not Started | TBD
D004 | Application | IaC Template Reference — Build Doc | Build Doc | TBD | Not Started | TBD
D005 | Application | CI/CD Pipeline — Build Doc | Build Doc | TBD | Not Started | TBD
D006 | Security | IAM Role Design — Build Doc | Build Doc | TBD | Not Started | TBD
D007 | Security | Threat Model Document | Security Doc | TBD | Not Started | TBD
D008 | Operationalisation | Incident Response Runbook | Ops Runbook | TBD | Not Started | TBD
D009 | Operationalisation | Email Delivery Failure Runbook | Ops Runbook | TBD | Not Started | TBD
D010 | Operationalisation | Resubscribe Email Addresses Runbook | Ops Runbook | TBD | Not Started | TBD
D011 | Compliance | Protected B Control Mapping | Compliance Doc | TBD | Not Started | TBD
D012 | Compliance | Audit Evidence Package | Compliance Doc | TBD | Not Started | TBD
D013 | Documentation | End-User Guide — Reading Health Alerts | User Guide | TBD | Not Started | TBD
D014 | Documentation | Architecture Overview Diagram | Diagram | TBD | Not Started | TBD

## Change Log
Change Log
Change ID | Date | Changed By | Phase | Description of Change | Approved By | Notes
CHG001 | 2026-03-06 | Project Lead | All | Initial project tracker created | TBD